## Potentially Feasible WMS
Template for Presenting Water Management Strategies Considered and Evaluated (see Exhibit C Section 2.5.1)
Every WUG Entity with an Identified Need |  | WMSs to be considered by statute1 | [11 empty] | Additional WMSs to be considered by rule
WUG Name | Maximum need 2030-2080 (af/yr) | conservation - water use reduction | conservation - water loss mitigation | drought management | reuse | management of existing supplies | development of large-scale marine seawater or brackish groundwater | conjunctive use | acquisition of available existing supplies | development of new supplies | development of regional water supply or regional management of water supply facilities | voluntary transfer of water (including regional water banks, sales, leases, options, subordination agreements, and financing agreements) | emergency transfer of water under Section 11.139 | system optimization, reallocation of reservoir storage to new uses, contracts, water marketing, enhancement of yield, improvement of water quality | new surface water supply | new groundwater supply | brush management; precipitation enhancement | interbasin transfers of surface water | aquifer storage and recovery | cancellation of water rights | rainwater harvesting | other
WUG A | 20000 | PF | PF | nPF | PF | PF | PF | PF | PF | PF | PF | PF | PF | PF | PF | nPF | nPF | nPF | nPF | nPF | nPF
WUG B | 5500 | PF | PF | PF | PF | nPF | PF | nPF | PF | PF | nPF | PF | nPF | PF | nPF | PF | nPF | nPF | PF | nPF | nPF
1 Texas Water Code §16.053(e)(5)
nPF = considered but determined 'not potentially feasible' (may include WMSs that were initially identified as potentially feasible)
PF = considered 'potentially feasible' and therefore evaluated
(all pertinent information for WMS evaluations must be presented in the regional water plan, including for WMSs considered potentially feasible but not recommended)

## WMS Implementation Status
Template for Documenting the Implementation Status of Certain WMSs (see Exhibit C Section 2.5.2.7)
REGIONAL WATER PLAN WMS/PROJECT DATA | [5 empty] | ANTICIPATED/ESTIMATED (OR ACTUAL1) IMPLEMENTATION ACTIVITIES AND DATES
Water Management Strategy/Project Name | Project Sponsor | WMS Project Sponsor Region | Online Decade | Capital Cost | Anticipated Footprint Acreage (acres) | SPONSOR AUTHORIZATION | PERMITTING STATUS (as applicable) | [8 empty] | PLANNING, DESIGN, AND CONSTRUCTION STATUS | [5 empty] | TOTAL FUNDS EXPENDED TO DATE | Other significant activities completed (summary)
[7 empty] | STATE WATER RIGHT STATUS |  |  |  | FEDERAL 404 PERMIT STATUS (if applicable) |  | DESALINATION PERMIT STATUS |  | OTHER KEY PERMITS | GEOTECH/DESIGN | LAND ACQUISITION |  | CONSTRUCTION
[6 empty] | Date(s) that the sponsor took an affirmative vote or other action to make expenditures necessary to construct or file applications for state or federal permits (date(s)) | Anticipated (or actual) TCEQ application filed (date) | Anticipated (or actual) State Water Right Permit Administratively Complete (date) | Anticipated (or actual) Draft State Water Right Permit Issued (date) | Anticipated (or actual) Date Final State Water Right Permit Issued (date) | Anticipated (or actual) application for permit filed (date) | Anticipated (or actual) permit issuance (date) | Anticipated (or actual) diversion permit issued (date) | Anticipated (or actual) Discharge/Disposal Permit Issued (date) | Summary of other permits and status (summary) | Generally describe the types and amount (as %s) of geotechnical/ reconnaissance/ engineering feasibility or other technical, testing, and/or design work etc. performed to date (summary) | Percent Land Acquisition Completed (%) | Anticiptated land acquisition completion (date) | Anticipated start of construction (Date) | Percent construction completed (%) | Anticipated construction completion (date) | Rough approximation of the total expenditures, to date, on ALL activities related to project implementation to date (millions of $s)
FOOTNOTE 1 : ANY DATE ENTERED THAT IS PRIOR TO ADOPTION OF THE REGIONAL WATER PLAN IS ASSUMED TO BE AN 'ACTUAL' DATE

## Measures for DWDOR
Template for types of water users most likely associated with measures that may provide some additional water supply capacity in the event of a near-term DWDOR (see Exhibit C Section 2.7.2)
|  | *Included in the adopted RWP | [9 empty] | **Measures that may be available beyond the recommended strategies identified in the adopted RWP
|  | Built-in conservative modeling or other assumptions |  |  |  |  | Additional recommendations for additional supplies beyond those needed to meet needs |  |  |  |  | Demand-management measures |  |  |  | Water supply measures
WUG/WWP Name | Applicable water supplies | 1-year safe yield used in surface water modeling*** | Utilizing MAG based upon a DFC developed under drought conditions | No return flows | Maximum permitted amounts | Other | Certain WMSs include 'management supply' | Other | Other | Other | Other | Implement drought management (not a recommended WMS) | Implement additional drought management measures beyond those in the plan, such as... | Other | Other | Implement recommended GW WMSs but earlier than shown in the plan | Pursue new direct potable reuse to extend existing supplies | Pursue new brackish desalination | Other | Other
Municipal WUG A | Reservoir X; Aquifer Z | X | [13 empty] | x
Municipal WUG B
Irrigation, County A
Steam-electric, County B
Mining, County A
Manufacturing, County B
Livestock, County A
etc
* Key assumptions, analyses, strategies, and projects that are already incorporated directly into the adopted regional water plan calculations and recommendations and that go beyond just meeting identified water needs anticipated under DOR conditions.
** Potential additional types of measures and responses, that are not part of the recommendations in the adopted regional water plan, but that would likely be available to certain water providers/users in the event of the near-term onset of a DWDOR and that would be capable of providing additional, potential capacity for those water providers and users to withstand a DWDOR.
*** Regions should edit the term "1-year" safe yield to reflect the definition of safe yield used by the planning group.

## Drought Triggers & Actions
Template for Existing Drought Trigger and Response Actions (see Exhibit C Section 2.7.4)
|  |  | SPECIFIC TRIGGERS | [9 empty] | SPECIFIC ACTIONS
|  |  | SOURCE MANAGER |  |  |  |  | USERS (e.g. WUGs) |  |  |  |  | SOURCE MANAGER |  |  |  |  | USERS (e.g. WUGs)
SOURCE NAME | TYPE (sw/gw) | Factor to be considered | Mild | Moderate | Critical | Severe | Emergency | Mild | Moderate | Critical | Severe | Emergency | Mild | Moderate | Critical | Severe | Emergency | Mild | Moderate | Critical | Severe | Emergency

## Potential Emergency Supplies
Template for Screening Potential Emergency Supplies (see Exhibit C Section 2.7.7)
Entity |  |  |  | Potential Emergency Water Supply Source(s) | [9 empty] | Implementation Requirements
Water User Group Name | County | 2030 Population | 2030 Demand (AF/year) | Release from upstream reservoir | curtailment of upstream/downstream water rights | local groundwater well | brackish groundwater limited treatment | brackish groundwater desalination | emergency interconnect | other named local supply | trucked-in water | (other) | (other) | Type of infrastructure required | Entity providing supply | Other local entities required to participate/ coordinate | Emergency agreements/ arrangements already in place? | other

## Scoping Task 5B
Template for Scoping Currently Contracted Task 5B Funding for Region-Specific Subtasks (See Exhibit C Section 2.5.6)
Strategy Type(s)
ASR | Conservation/Drought Management | Groundwater Desal | Groundwater Dvlp | Reuse | New Major Reservoir | Other Surface Water | Seawater Desal | Conjunctive Use | Other WMS (Subordination, etc) | Region | Overall TWDB Task Number | SubTask WMS evaluation number | SubTask WMS | SubTask Scope of Work Write-up | Deliverable | SubTask Budget ($) | WUG(s) &/OR WWP Entities Potentially Served by WMS(s) | Addressing a changed condition from previous cycle? If yes, describe the changed condition. | When was this WMS identified by RWPG as potentially feasible? | Was the WMS evaluated in any previous Regional Water Planning Cycles? | Is evaluation a limited update to previous technical evaluation information? If no, indicate specific update in subtask sow column E
[11 empty] | 5B | 1 |  |  |  | 0
[11 empty] | 5B | 2 |  |  |  | 0
[11 empty] | 5B | 3 |  |  |  | 0
[11 empty] | 5B | 4 |  |  |  | 0
[11 empty] | 5B | 5 |  |  |  | 0
[11 empty] | 5B | 6 |  |  |  | 0
[11 empty] | 5B | 7 |  |  |  | 0
[11 empty] | 5B | 8 |  |  |  | 0
[11 empty] | 5B | 9 |  |  |  | 0
[14 empty] | REGION-SPECIFIC SUBTASKS TOTAL BUDGET |  | 0

## Scoping Task 5B Ex. Filled In
Template Example Filled in for Scoping Currently Contracted Task 5B Funding for Region-Specific Subtasks (See Exhibit C Section 2.5.6)
Strategy Type(s)
ASR | Conservation/Drought Management | Groundwater Desal | Groundwater Dvlp | Reuse | New Major Reservoir | Other Surface Water | Seawater Desal | Conjunctive Use | Other WMS (Subordination, etc) | Region | Overall TWDB Task Number | SubTask WMS evaluation number | SubTask WMS | SubTask Scope of Work Write-up | Deliverable | SubTask Budget ($) | WUG(s) &/OR WWP Entities Potentially Served by WMS(s) | Addressing a changed condition from previous cycle? If yes, describe the changed condition. | When was this WMS identified by the RWPG as potentially feasible? | Was the WMS evaluated in any previous Regional Water Planning Cycles? | Is evaluation a limited update to previous technical evaluation information? If no, indicate specific update in subtask sow column N
|  | X | [7 empty] | X | 5B | 1 | Example Only: Update Groundwater Desalination WMS | Update previously recommended groundwater desalination WMSs in consideration of new MAG values and costing guidance. Updates include cost estimates and yield allocations. | Updated engineering & costing considerations appropriate to meet requirements for the 5th cycle of planning; and corresponding data submittal through the DB27 interface. | $$$ | WUGs X, Y, Z; WWP 1, 2 | Yes - updated MAGs | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | Yes
|  | X | [7 empty] | X | 5B | 2 | Example Only: Regional Brackish groundwater development | Evaluate the potential for a brackish groundwater desalination project to meet needs in "T", "U", and "V" counties. Evaluate layout of facilities (wells, well field collection system, pump stations, transmission pipelines, WTP, etc) necessary to deliver treated water to interested regional provider members, comprised of WUGs in these three counties. | New WMS/WMSP documentation will include description and discussion of planned facilities, firm DOR supply, environmental factors, engineering & costing considerations, and implementation issues. Corresponding data will be submitted through the DB27 interface. | $$$ | WUGs X, Y, Z; WWP 1, 2 | No | October 11, 2023 RWPG Meeting | No - new WMS to evaluate for the 2026 Plan | No
|  |  | X | [6 empty] | X | 5B | 3 | Example Only: Update Groundwater Development WMS | Update previously recommended groundwater development WMSs in consideration of new MAG values and costing guidance; but no other changed conditions. Updates include cost estimates and yield allocations. | Updated engineering & costing considerations appropriate to meet requirements for the 5th cycle of planning; and corresponding data submittal through the DB27 interface. | $$$ | WUGs A, B, C; WWP 3, 4 | No | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | Yes
|  |  | X | [6 empty] | X | 5B | 4 | Example Only: Regional Aquifer Supplies | Update evaluation to include water supplies potentially available from groundwater sources in "S" County and "Y" County and evaluation of transmission, treatment, and integration facilities necessary for delivery to "Metro" City, "Uptown", and a WWP service area within "S" County-Other. Will utilize the updated TWDB costing tool to calculate revised project costs. | WMS/WMSP documentation will include updated description and discussion of planned facilities, firm DOR supply, environmental factors, engineering & costing considerations, and implementation issues. Corresponding data will be submitted through the DB27 interface. | $$$ | "Metro" and "Uptown" Utilities, and "S" County-Other | Yes, changes in well field locations, transmission line paths, and updated yields | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | No
|  |  | X | [6 empty] | X | 5B | 5 | Example Only: "ZZ" PUA – Phases 1 & 2 | Coordinate with the "ZZ" PUA to determine current plans regarding this WMS. Update/revise technical evaluation to include information regarding current groundwater permit status with due consideration of MAG, delivery locations, and timeframe for phasing and implementation. Update phase quantities as they coincide with end user demands. Update estimated cost of project(s) and technical evaluation documentation. | Update of WMS documentation will include description and discussion of planned facilities, firm DOR supply, environmental factors, engineering & costing considerations, and implementation issues. Corresponding data will be submitted through the DB27 interface. | $$$ | Utilities "Smalltown", "YY", "Nearby", and Others | Yes - permits granted | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | No
| X | [8 empty] | X | 5B | 6 | Example Only: Update Multiple Advanced Water Conservation Strategies | Update the Municipal, Irrigation, Industrial, Steam-Electric, and Mining water use categories advanced water conservation WMSs using the applicable subset from the general procedures and Best Management Practices (BMPs) starting with the 2021 Region X recommended WMSs and accounting for more current estimates of municipal per capita use, irrigation application rates, and BMP implementation costs, etc. As is required, these RWPG recommendations shall be assumed to be the “highest practicable level” of conservation for WUGs/ WWPs that are dependent upon WMSs involving an interbasin transfer(s). Each WMSP with a capital cost will be presented separately in the 2026 Plan and DB27. | Update of WMS/WMSP documentation will include description and discussion of planned facilities, firm DOR supply, environmental factors, engineering & costing considerations, and implementation issues. Corresponding data will be submitted through the DB27 interface. | $$$ | All Municipal WUGs and potentially other non-municipal WUGs (as needed) | No | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | No
[6 empty] | X |  |  |  | X | 5B | 7 | Example Only: Update Reuse WMS | Update previously recommended reuse WMSs with no other changed conditions than updated costing guidance. Updates include cost estimates and yield allocations. | Updated engineering & costing considerations appropriate to meet requirements for the 5th cycle of planning; and corresponding data submittal through the DB27 interface. | $$$ | WUGs X, Y, Z; WWP 1, 2 | No | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | Yes
|  |  |  | X | [5 empty] | X | 5B | 8 | Example Only: Reuse Strategies | Coordinate with WMS sponsors regarding the status of their independent WMSs. Each of these WMSs and their associated projects will be presented separately in the 2026 Plan and DB27. Update technical details, yields, costs, and other appropriate factors as applicable. Strategies include reuse for "Bigcity", "W" County MUDs 8 and 9, and wastewater reclamation for municipal irrigation. | Technical memoranda describing WMSs/WMSPs and summarizing as applicable supply sources and quantities, sponsors and users, facility locations, implementation schedule, cost, issues and considerations regarding implementation, and relevant references. Corresponding data will be submitted through the DB27 interface. | $$$ | WUGs X, Y, Z; WWP 1, 2 | Yes: Varies by project - see attached scope of work details | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 and 2016 plans | Yes
|  | X | [7 empty] | X | 5B | 9 | Update Other Surface Water WMS | Update previously recommended other surface water WMSs with no other changed conditions. Updates include cost estimates and yield allocations. | Updated engineering & costing considerations appropriate to meet requirements for the 5th cycle of planning; and corresponding data submittal through the DB27 interface. | $$$ | WUGs A, B, C; WWP 3, 4 | No | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 Plan | Yes
[9 empty] | X | X | 5B | 10 | Example Only: Various WMS costs (no other changes) | Update cost estimates and documentation of the following 7 WMSs to be consistent with TWDB rules and guidance (WMSs listed here as "a"- "g"). Each of these WMSs will be presented separately in the 2026 Plan and DB27 as is required. Some costs will be calculated using the updated TWDB costing tool, others with more detailed project-specific costs. | Update previously alternative projects to now be recommended; and update all WMSP technical documentation, including updated costs, for inclusion in 2021 plan. Corresponding data will be submitted through the DB27 interface. | $$$ | WUGs A, B, C; WWP 3, 4 | No | October 11, 2023 RWPG Meeting | Yes, recommended WMS in 2021 and 2016 plans | Yes
X | [5 empty] | X |  |  |  | X | 5A | 11 | Example Only: Storage above Reservoir "Z" | Reassess technical evaluations of Storage above Reservoir "Z" (Surface or ASR) – Evaluate three (3) potential surface water storage sites in the watershed above Reservoir "Z". Evaluated the firm yield of using reservoir surface water storage to firm-up run-of-river water availability (firm diversion) under a new appropriation. Also assess capability of Aquifer "W" to store surface water available under a new appropriation in "Q" and "R" counties in two (2) potential well field areas. Evaluate the firm supply available. Will utilize the updated TWDB costing tool to provide updated project costs. | Recommended WMS/WMSP documentation will include description and discussion of planned facilities, WMS firm DOR supply, environmental factors, and implementation issues from the previous alternative WMS evaluation; along with updated engineering & costing considerations appropriate to meet requirements for the 5th cycle of planning; and corresponding data submittal through the DB27 interface. | $$$ | "Bigtown" Utility | No | October 11, 2023 RWPG Meeting | Yes, alternative WMS in 2021 Plan | Yes
[14 empty] | REGION-SPECIFIC SUBTASKS TOTAL BUDGET |  | 0

## Cost_Estimate_delete (hidden)
Potential costs generally associated with FMSs, FMPs, and FMEs
Non-recurring | Study costs and other (non-capital costs) | Non-engineering studies: (e.g., flood plain regulation development; flood authority or revenue raising studies; public awareness program) | x | x
|  | Engineering/technical/feasibility studies: (e.g. Hydrologic & hydraulic model development/modelling/mapping; identification of potential flood risk reduction solutions; BCA and alternative analyses; project design; construction engineering) |  | x | x
Surveying; geotechnical; testing
| Total study costs |  | x | x | x
| Construction-related (capital costs) | Design and Permitting |  | x
|  | Environmental; archaeological & historical resources |  | x
|  | Temporary and/or permanent easements; land acquisition |  | x
|  | Mitigation; utility relocation |  | x
|  | Surveying; geotechnical; testing |  | x
|  | Legal assistance; fiscal services & costs (bond counsel); outreach |  | x
|  | Direct construction costs of components/facilities |  | x
|  | Buyouts; property elevations |  | x
|  | Interest during construction |  | x
|  | Project management (by engineer) |  | x
|  | Inspection; pilot testing; warranty; manuals |  | x
|  | (other special services or relevant costs) |  | x
| *Total construction costs | Contingency(s) |  | x
TOTAL PROJECT COSTS |  |  |  | x
Recurring |  |  |  | x
|  | Debt service [interest rate & term (years)] |  | x
|  | *Operation & Maintenance |  | x
TOTAL ANNUAL COSTS |  | *Other (i.e., public awareness campaign) | x | x
| * Generally to be used as an input into the BCA |  | x | x
We need to include design and permitting
This happens in feasibility, preliminary engineering and design phase.
From reem: Matt, This looks good. I would probably break down and rearrange a few of the cost items but you touched all of the key items. I would add project management, engineering design, permitting, inspection and real estate costs. Here is an outline of the steps involved in a flood risk reduction construction project mostly in chronological order except Item #10: 1. Problem area identification 2. Flood Risk Quantification a. Hydrologic Modeling b. Hydraulic Modeling c. Mapping 3. Problem area prioritization 4. Feasibility Study * Some entities do #4 and #5 together 5. Preliminary Engineering a. Survey b. Alternative Analysis – includes modeling c. Environmental, utility conflicts, identification of permitting requirements including historic, archeological, endangered species etc. d. Recommended solution identification – often includes 30% Design for storm drain projects to capture utility conflicts 6. Engineering Design a. Survey b. Design – 30%, 60%, 90% and 100% c. Permitting 7. Easement acquisition and/ or property acquisition 8. Construction a. Direct Construction Cost i. Construction of storm drain systems, detention ponds, diversion channels/ tunnels, flood walls, drainage ditch, ii. Upgrade of LWCs iii. Buyouts including relocation cost, demolition, abatement etc., iv. Property elevation v. Dam modernization b. Contingency c. Construction phase services d. Inspection 9. Post Construction a. Inspection and warranty 10. Other Costs a. Public outreach throughout the process including educational materials b. Legal cost c. Real estate cost (this is significant for property acquisition/ buy-out projects). Thanks, Reem